## Fico
CHALLENGER Implementation-FiCo
| Start Date | 2021-07-28 |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40
| Project Manager | Saurabh Jog | [5 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25
 | time axis 2021-07-26 to 2022-05-01
WBS | PROJECT | Task Lead | START | END | DAYS | % DONE | WORK DAYS | time axis 2021-07-26 to 2022-05-01
1 | Masters -Create/Alter/View with user rights |  | 2021-07-28 | 2021-08-31 | 34 | 10% | 25
1.1 | User Roles & Users |  | 2021-07-28 | 2021-08-18 | 21 | 10% | 16
1.2 | A/c Schedule |  | 2021-07-28 | 2021-08-18 | 21 | 10% | 16
1.3 | A/c Master |  | 2021-07-28 | 2021-08-18 | 21 | 10%
1.4 | Currency & rates Master |  | 2021-07-28 | 2021-08-18 | 21 | 10%
1.5 | Cost Centre |  | 2021-07-28 | 2021-08-18 | 21 | 5%
1.6 | Opening Balance |  | 2021-08-19 | 2021-08-31 | 12 | 5%
1.7 | Budget -P&L |  | 2021-08-19 | 2021-08-31 | 12 | 5%
1.8 | Budget Cash flow |  | 2021-08-19 | 2021-08-31 | 12 | 5%
1.9 | Cash flow- payment & receipts types |  | 2021-08-19 | 2021-08-31 | 12 | 5%
1.10 | LC master |  | 2021-08-19 | 2021-08-31 | 12 | 5%
1.11 | Balance sheet formatting |  | 2021-08-19 | 2021-08-31 | 12 | 0% | 9
2 | Transactions -Create/Alter/View with user rights |  | 2021-09-01 | 2021-09-30 | 15 | 0% | 22
2.1 | Bank Payments |  | 2021-09-01 | 2021-09-20 | 19 | 0% | 14
2.2 | PDC cheques Issue |  | 2021-09-01 | 2021-09-20 | 19 | 0% | 14
2.3 | Prepayments LC |  | 2021-09-01 | 2021-09-20 | 19 | 0% | 14
2.4 | Cash Payments |  | 2021-09-01 | 2021-09-20 | 19 | 0% | 14
2.5 | Cash Receipts |  | 2021-09-01 | 2021-09-20 | 19 | 0% | 14
2.6 | Purchase |  | 2021-09-01 | 2021-09-20 | 19 | 0%
2.7 | Sales |  | 2021-09-01 | 2021-09-20 | 19 | 0%
2.8 | Debit Note |  | 2021-09-01 | 2021-09-20 | 19 | 0%
2.9 | Credit Note |  | 2021-09-01 | 2021-09-20 | 19 | 0%
2.10 | Journal Voucher |  | 2021-09-01 | 2021-09-20 | 19 | 0%
2.11 | Bank Reconciliation |  | 2021-09-21 | 2021-09-25 | 4 | 0%
2.12 | PDC Clearance |  | 2021-09-21 | 2021-09-26 | 5 | 0%
2.13 | LC register Update |  | 2021-09-21 | 2021-09-27 | 6 | 0%
2.14 | Unadjusted bills knockoff |  | 2021-09-15 | 2021-09-30 | 15 | 0% | 12
3 | Reports- screen, pdf, excel, csv |  | 2021-10-01 | 2021-10-20 | 19 | 0% | 14
3.1 | Registers- for each Transaction Type |  | 2021-10-01 | 2021-10-15 | 14 | 0% | 11
3.2 | Voucher Printing- For each Transaction Type |  | 2021-10-01 | 2021-10-16 | 15 | 0% | 11
3.3 | Masters listing- all types |  | 2021-10-02 | 2021-10-17 | 15 | 0% | 10
3.4 | A/c - Ledger, Trial Balance, PL , Balance sheet |  | 2021-10-03 | 2021-10-18 | 15 | 0% | 11
3.5 | Cash Flow |  | 2021-10-04 | 2021-10-18 | 14 | 0%
3.6 | Budget Vs Actual- P&L |  | 2021-10-05 | 2021-10-18 | 13 | 0%
3.7 | Budget Vs Actual- Cash Flow |  | 2021-10-06 | 2021-10-18 | 12 | 0%
3.8 | Receivable Reports- aging ,o/s |  | 2021-10-07 | 2021-10-18 | 11 | 0%
3.9 | Payables Reports- Aging, o/s |  | 2021-10-08 | 2021-10-18 | 10 | 0%
3.10 | Dash Boards with graphical presentation |  | 2021-10-09 | 2021-10-20 | 11 | 0% | 8
4 | Accounting Functionality |  | 2021-10-21 | 2021-10-25 | 4 | 0% | 3
4.1 | Year End Closing & balance c/f |  | 2021-10-21 | 2021-10-25 | 4 | 0% | 3
4.2 | Transactions Authorisation |  | 2021-10-21 | 2021-10-25 | 4 | 0% | 3
4.3 | auto email reminders for receivables |  | 2021-10-21 | 2021-10-25 | 4 | 0% | 3
5 | User Acceptance testing |  | 2021-10-26 | 2021-10-30 | 4 | 0% | 4
5.1 | overall testing before go live |  | 2021-10-26 | 2021-10-30 | 4 | 0% | 4
Note on A6: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on C6: Task Lead Enter the name of the Task Lead in this column.
Note on D6: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on E6: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on F6: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on G6: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H6: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## schedule
Stories
BackEnd | team | task | start | days | end | remarks | % Completion | LC
Harsh | Jevin | Ledger Balance & BRS-Backend | 2021-08-11 | 2 | 2021-08-13 | Backend | 100% | Ledgers | Head,Group,Ledger
Jevin | Ayush | Budget-Backend | 2021-08-11 | 2 | 2021-08-13 | Backend | 100% | Ledger Balances | Ledger , Billwise & BRS
Ayush | Jevin | Tools- Download(Excel,CSV) Data Table | 2021-08-14 | 1 | 2021-08-15 | all data table | 50% | Cost Centers
| Ayush | (LC Master) | 2021-08-14 | 2 | 2021-08-16 | all trasactions/ entries | 40% | Currency
| Jevin | Deploy on Azure Server | 2021-08-16 | 4 | 2021-08-20 | live testing, entire project | 0% | Vouchers
Front End | Shaunak | Basic Menu for each Company | 2021-08-11 | 1 | 2021-08-12 | Screen | 100% | Budget
| Jainam | Data table & Normal Table | 2021-08-11 | 2 | 2021-08-13 |  | 100%
Jainam | Chirayu | Ledgers-CRUD Frontend | 2021-08-11 | 7 | 2021-08-18 | Heading, Groups & Ledger | 60%
Chirayu | Shaunak | Cost Centers -CRUDFront End | 2021-08-13 | 3 | 2021-08-16 | Categories, Cost Center | 90%
Shaunak | Jainam | Currency- CRUD Frontend | 2021-08-14 | 1 | 2021-08-15 |  | 90%
| Jainam | Voucher Types- CRUD Front End | 2021-08-16 | 3 | 2021-08-19 |  | 20% | Data Table
| Shaunak | LC-CRUD FrontEnd | 2021-08-17 | 2 | 2021-08-19 | LC Master & Amendment to LC |  | Normal Table | Pagination
| Chirayu | Ledger Balance Frontend | 2021-08-19 | 3 | 2021-08-22 | Ledger Balance & Billwise |  |  | Sort
| Jainam | BRS CRUD-Frontend | 2021-08-20 | 2 | 2021-08-22 |  |  |  | find
| Chirayu | Budget CRUD-Frontend | 2021-08-23 | 3 | 2021-08-26 | P&L Budget & Cash Flow Budget
| Jainam | Help | 2021-08-27 | 1 | 2021-08-28 | Add Help HTML on frontend & for each menue/page
| K,J,H | Rectify -Company,Users | 2021-08-15 | 3 | 2021-08-18 | test report & acceptance
| K,J,H | Rectify -Ledgers,Cost Centers, Vouchers | 2021-08-23 | 2 | 2021-08-25 | test report & acceptance
| K,J,H | Rectify -LC,Opening Balance, Budget | 2021-08-29 | 3 | 2021-09-01 | test report & acceptance
| Kiran | Testing - Company & Users | 2021-08-10 | 4 | 2021-08-14 | Test, Report.
| Kiran | Company,Users-Help File | 2021-08-15 | 4 | 2021-08-19 | this document will outline exact requirements
| Kiran | Testing Ledgers,Cost Centers, Vouchers | 2021-08-20 | 2 | 2021-08-22 | Test, Report.
| Kiran | Help File-Ledgers Cost Centers, Vouchers | 2021-08-23 | 2 | 2021-08-25 | this document will outline exact requirements
| Kiran | Testing-LC | 2021-08-20 | 1 | 2021-08-21 | Test, Report.
| Kiran | Testing- Opening Balance | 2021-08-23 | 1 | 2021-08-24 | Test, Report.
| Kiran | Testing - Budget | 2021-08-27 | 1 | 2021-08-28 | Test, Report.
| Kiran | Help File-LC,Opening Balance ,Budget | 2021-09-02 | 2 | 2021-09-04 | this document will outline exact requirements
100%
Formulas:
end = [days]+[start]
end = [start]+[days]
start = [end, row above]+1

## menus
Menu | Sub Menu | Sub-Sub
Masters | Ledger Master | Head
Group
Ledger
Opening Balance
| Cost Center | Cost Category
Cost Center
| Budget | P&L Budget
Cash Flow Budget
Voucher Types
Currency
| LC | Import
Export
Transactions | Receipt | Cash Receipt
Bank Receipt
PDC Receipt
| Payment | Cash Payment
Bank Payment
PDC Payment
| Purchase | Cash Purchase
Credit Purchase
| Sales | Cash Sales
Credit Sales
Debit Note
Credit Note
Contra
Journal
Memo
Bank Reconcilation
PDC / Cheque Clearance
Unadjusted bills knockoff
Prepayments LC
Reports | Dash Board
Receivable
Payable
GL
PL
Cash Flow
Budget
Tools | Close A/c Year
Start Year
Activity Log
Help

## 1_Construction Program (hidden)
CHALLENGER Implementation
| Start Date | 2021-04-01 |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40
| Project Manager | Saurabh Jog | [5 empty] | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10 | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27
 | time axis 2021-03-29 to 2022-01-02
WBS | PROJECT | Task Lead | START | END | DAYS | % DONE | WORK DAYS | time axis 2021-03-29 to 2022-01-02
1 | QIV : 2020 : Search of ERP System |  | 2020-11-01 | 2021-01-19 | 79 | 100% | 57
1.1 | Search of ERP |  | 2020-11-01 | 2020-12-11 | 40 | 100% | 30
1.2 | Scope Discussions with ERP Supplier |  | 2020-12-13 | 2021-01-02 | 20 | 100% | 15
1.3 | Collection of Final Quote From ERP Supplier |  | 2021-01-04 | 2021-01-19 | 15 | 100% | 12
2 | QI : 2021 : ERP Evaluation |  | 2021-01-20 | 2021-03-17 | 56 | 100% | 41
2.1 | Comparison of all Identified ERP : Features & Costing |  | 2021-01-20 | 2021-02-19 | 30 | 100% | 23
2.2 | Shortlisting of ERP |  | 2021-02-20 | 2021-02-27 | 7 | 100% | 5
2.3 | Presentation to Management of Selected ERP |  | 2021-03-06 | 2021-03-06 | 0 | 100% | 0
2.4 | Approval from Management |  | 2021-03-07 | 2021-03-09 | 2 | 100% | 2
2.5 | Personal Visit to ERP Supplier Office to Kerala |  | 2021-03-14 | 2021-03-17 | 3 | 100% | 3
2.6 | Signing of Contract & Release of PO |  | 2021-03-22 | 2021-04-01 | 10 | 100% | 9
3 | QII : 2021 : First Phase of Project |  | 2021-04-02 | 2021-07-10 | 99 | 76% | 71
3.1 | Preparation of Product Data : Milestone 1 |  | 2021-04-02 | 2021-05-02 | 30 | 100% | 21
3.2 | Development of Masters : Product Formula & Other : Milestone 2 | Arun | 2021-05-03 | 2021-06-09 | 37 | 100% | 28
3.3 | Release of Milestone 2 | Arun | 2021-06-10 | 2021-06-10 | 0 | 100% | 1
3.4 | Data Entry of Master in System : Product Group, Product Categeory, Parameters & Configurations | Amal | 2021-06-12 | 2021-06-24 | 12 | 100% | 9
3.5 | Grilles & Damper Old Part Codes | Numaan | 2021-06-23 | 2021-06-24 | 1 | 50%
3.6 | Data Entry of Grilles & Damper Old Part Code in System | Arun | 2021-06-25 | 2021-06-25 | 0 | 50%
3.7 | Forumula Master BOM - For Balance Produts | Ronak | 2021-06-24 | 2021-06-28 | 4 | 60%
3.8 | Forumula Master Entry & Mapping | Amal | 2021-06-26 | 2021-07-04 | 8 | 50%
3.9 | Sale Module : Quote & SO Format - Development : Milestone 3 | Arun | 2021-06-20 | 2021-06-27 | 7 | 100%
3.10 | Release of Milestone 3 | Arun | 2021-06-28 | 2021-06-28 | 0 | 100% | 1
3.11 | Development : Part Code Generation Program as Per New Logic | Arun | 2021-06-28 | 2021-06-30 | 2 | 80% | 3
3.12 | New Part Code Creation & Mapping to the Old Part Code. | Numaan / Kiran | 2021-07-01 | 2021-07-09 | 8 | 50% | 7
3.13 | Testing & Implementation of Sales Module : Quotation & Sales Order | Numaan/ Arun | 2021-06-30 | 2021-07-10 | 10 | 50% | 8
4 | QIII : 2021 : Second Phase of Project |  | 2021-07-11 | 2021-09-29 | 80 | 0% | 58
4.1 | Parallel Run with Visacc : Sales Module | Sonakshi | 2021-07-11 | 2021-08-10 | 30 | 0% | 22
4.2 | Development of Production & Procurement Module : Grilles & Damper : Milestone 4, 5, 6 & 7 | Arun | 2021-07-01 | 2021-07-31 | 30 | 60% | 22
4.3 | Release of Milestone 4,5,6 & 7 | Arun | 2021-08-01 | 2021-08-01 | 11 | 0% | 0
4.4 | Testing & Implementation of Production Module : Grilles & Damper | Numaan / Arun | 2021-08-02 | 2021-08-12 | 10 | 0% | 9
4.5 | Parallel Run with Visacc : Production Module : Grilles & Damper |  | 2021-08-13 | 2021-09-27 | 45 | 0% | 32
4.6 | Development of Production Module : Ducting : Milestone 8 & 9 |  | 2021-08-13 | 2021-09-12 | 30 | 20% | 21
4.7 | Release of Milestone 8 & 9 |  | 2021-09-13 | 2021-09-13 | 30 | 0% | 1
4.8 | Testing & Implementation of Production Module : Ducting |  | 2021-09-14 | 2021-09-29 | 15 | 0% | 12
5 | QIV : 2021 : Final Phase of Project |  | 2021-10-16 | 2021-12-27 | 72 | 0% | 51
5.1 | Parallel Run with Visacc : Ducting Module |  | 2021-09-30 | 2021-11-14 | 45 | 0% | 32
5.2 | Development of Submittal Module : Milestone 10 |  | 2021-09-30 | 2021-10-15 | 15 | 0% | 12
5.3 | Release of Milestone 10 : Submittal Module |  | 2021-10-16 | 2021-10-16 | 0 | 0% | 0
5.4 | Implementation of Submittal Module |  | 2021-10-17 | 2021-10-27 | 10 | 0% | 8
5.5 | Rectification works |  | 2021-10-28 | 2021-12-27 | 60 | 0% | 43
QIV
QII
QIII
QIV
QI
Note on A6: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on C6: Task Lead Enter the name of the Task Lead in this column.
Note on D6: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on E6: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on F6: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on G6: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on H6: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Sheet1 (hidden)
approval for tcjnical submittal | 2021-05-20
shipment of mockup | 31st May
receipt of mockp | 2021-06-05
Inspection of Mockup | 2021-06-08
Approval of Mockup | 2021-06-24
First Shipmnt | 2021-07-05 | 50 | 2021-07-02 | 2021-06-25 | 7
| 2021-07-12 | 50
| 19/07/201 | 50
| 2021-07-26 | 50

## Help (hidden)
Help
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
About This Template
This Gantt Chart Template provides an easy way to create a simple project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos of the Pro Version on Vertex42.com
Please read the license agreement in the TermsOfUse worksheet to learn how you may or may not use and share this spreadsheet.
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments to provide extra information. | Label
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• Insert new tasks using one of the methods listed below.
| • Define the task start date and duration (days) by editing the light green cells. | Input Cell
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Help improve Excel by voting on a suggestion to fix this problem.
Using the Template Rows and Choosing a WBS Level
The set of template rows at the bottom of the Gantt Chart worksheet provide examples of different ways to format and define tasks for different WBS levels.
Each different WBS level uses a different formula in the WBS column.
You can either copy/paste/insert these template rows via Method 2 as explained above, OR you can just copy/paste the desired WBS cell when you want to change the WBS level.
If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter the WBS numbers if you want to.
You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color. The Pro version includes a column where you can change the color by entering a color code ("b"=blue, "g"=green, etc.)
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is a feature of the Pro version. There is nothing in the free version preventing you from entering your own formulas, though.
Q: | How do I calculate Calendar Days after entering the Start and End Dates?
You can calculate the duration in calendar days (including both start and end dates) using the formula =enddate-startdate+1
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | How do I create a summary row that shows the MIN and MAX dates for all sub-tasks?
In the Start column, use the formula =MIN(range_of_start_dates)
In the End column, use the formula =MAX(range_of_end_dates)
In the Days column, use the formula =end_date-start_date+1
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a group of tasks can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2006-2018 Vertex42 LLC
Note on C16: This is an example comment.